## Functional Requirements
Epic 1 — Mobility Opportunity Management
ID | User Story | Priority
US-001 | As a Mobility Coordinator, I want to publish a mobility opportunity with its destination, period and available places so that students can apply to it. | Must
US-002 | As a Mobility Coordinator, I want to define the eligibility requirements of each opportunity (minimum GPA, completed credits, language level) so that validation reflects each destination. | Must
US-003 | As a Mobility Coordinator, I want to define the required document set per opportunity so that students know exactly what to submit. | Must
US-004 | As a Mobility Coordinator, I want to update an opportunity and keep a version history of its requirements so that applications submitted earlier remain traceable to the rules that applied to them. | Must
US-005 | As a Mobility Coordinator, I want to open and close the application period of each opportunity independently. | Should
US-038 | As a Mobility Coordinator, I want to register a change proposed by a partner university for one of its opportunities, so that it is recorded and classified as material or non-material. | Must
US-039 | As a Mobility Coordinator, I want to see an impact preview of a proposed change (applications by state, nominations to revoke, places released, notices to send) and confirm it, so that no application is returned by mistake. | Must
US-040 | As a Mobility Coordinator, I want to open a new application period when a confirmed material change returns applications, so that affected students can apply again. | Must
Epic 2 — Student Application
ID | User Story | Priority
US-006 | As a Student Applicant, I want to see the opportunities I am eligible for so that I do not apply to destinations I cannot access. | Should
US-007 | As a Student Applicant, I want to create and save a draft application before submitting it. | Must
US-008 | As a Student Applicant, I want to submit my application for review through a single entry point. | Must
US-009 | As a Student Applicant, I want to track the status of my application and the next action expected from me. | Must
US-010 | As a Student Applicant, I want to withdraw my application with a recorded reason. A return caused by a confirmed partner change is recorded separately from a withdrawal. | Should
US-011 | As a Student Applicant, I want to start a new application for a different destination while keeping my other applications, because a destination change is a new application. | Could
US-042 | As a Student Applicant whose approved application was returned by a partner change, I want priority when I apply again, so that I am not penalised for a change I did not cause. | Should
US-047 | As a Student Applicant, I want to correct and resubmit a rejected application while the application period is still open. | Should
US-048 | As a Student Applicant, I want to hold several active applications at the same time. | Must
Epic 3 — Eligibility and Document Validation
ID | User Story | Priority
US-012 | As the system, I want to validate GPA and completed credits against the requirements of the opportunity using Student Information System data. | Must
US-013 | As a Student Applicant, I want to upload required documents and see which are missing, pending, accepted or rejected. | Must
US-014 | As the system, I want to keep a version history of each uploaded document so that replacements do not erase the previous evidence. | Must
US-015 | As the system, I want to flag documents that expire before the mobility start date. | Should
US-016 | As a Mobility Adviser, I want to accept or reject a document with a recorded reason. | Must
Epic 4 — Review and Academic Approval
ID | User Story | Priority
US-017 | As a Mobility Adviser, I want to triage submitted applications for completeness before academic review reaches the faculty. | Must
US-018 | As a Mobility Adviser, I want to request corrections from the student and have the request recorded against the application. | Must
US-019 | As an Academic Program Coordinator, I want to review the course-equivalency plan and record an academic decision with comments. | Must
US-020 | As the system, I want to route each application according to opportunity type, destination and academic programme so that the correct reviewers are involved. | Must
Epic 5 — Nomination and Host Decision
ID | User Story | Priority
US-021 | As a Mobility Coordinator, I want to nominate validated candidates to a partner university. | Must
US-022 | As the system, I want to prevent nominations that exceed the available places of an opportunity. | Must
US-023 | As a Mobility Coordinator, I want to override a quota limit only with a mandatory recorded justification. | Should
US-024 | As a Mobility Coordinator, I want to record the admission or rejection decision returned by the host university. | Must
US-025 | As a Student Applicant, I want to see clearly whether I have been nominated by Horizon, admitted by the host university, or have accepted the mobility myself. | Must
US-043 | As a Student Applicant, I want to accept or decline an offer admitted by a host university within an offer window. | Must
US-044 | As the system, I want to expire offers not answered within the window and release their places. | Should
US-045 | As the system, I want to withdraw a student's other active applications of the same term, and release their places, when the student accepts a mobility. | Must
US-046 | As a Mobility Coordinator, I want to register the candidates chosen by the partner university, so that only chosen candidates are nominated when valid candidates exceed the places. | Should
Epic 6 — Pre-departure Preparation
ID | User Story | Priority
US-026 | As a Mobility Adviser, I want to track a pre-departure checklist for each student who accepted a mobility, covering visa evidence, insurance and briefing attendance. | Must
US-027 | As a Student Applicant, I want to upload visa and travel insurance evidence. | Should
US-028 | As the system, I want to notify students of upcoming pre-departure deadlines. | Should
Epic 7 — Notifications and Deadlines
ID | User Story | Priority
US-029 | As a Student Applicant, I want to be notified whenever my application changes status. | Should
US-030 | As a Mobility Adviser, I want to be notified of the applications pending my review. | Should
US-031 | As the system, I want to send deadline reminders based on both Horizon and partner-institution deadlines. | Should
US-041 | As the system, I want to notify every concerned party (the student, the responsible adviser, the academic coordinators and the mobility coordinator) of a returned application, stating what changed, that the process must be redone and the new deadline. | Must
Epic 8 — Reporting and Audit
ID | User Story | Priority
US-032 | As a Mobility Coordinator, I want an operational report of pending, incomplete, delayed and at-risk applications. | Must
US-033 | As the system, I want to record every status transition, decision and override in an immutable audit history. | Must
US-034 | As a Mobility Coordinator, I want to see the utilisation of available places by opportunity and destination. | Should
Epic 9 — Integrations and Identity
ID | User Story | Priority
US-035 | As the system, I want to authenticate users through the institutional identity provider. | Must
US-036 | As the system, I want to retrieve academic record data from the simulated Student Information System. | Must
US-037 | As a Mobility Coordinator, I want to record partner decisions, candidate selections and proposed changes through a simulated partner-university portal. | Should

## Product Backlog
ID | Epic | Story | Priority | Story Points | Sprint | Status
US-001 | Opportunity | Publish mobility opportunity | Must | 5 | 1 | Ready
US-002 | Opportunity | Define eligibility requirements | Must | 8 | 1 | Ready
US-007 | Application | Create draft application | Must | 5 | 1 | Ready
US-008 | Application | Submit application | Must | 5 | 1 | Ready
US-012 | Validation | Automated eligibility validation | Must | 13 | 2 | Ready
US-013 | Validation | Document upload and status | Must | 8 | 2 | Ready
US-016 | Validation | Accept or reject document | Must | 5 | 2 | Ready
US-017 | Review | Adviser completeness triage | Must | 8 | 2 | Ready
US-019 | Review | Academic equivalency review | Must | 8 | 3 | Draft
US-020 | Review | Review routing by programme | Must | 13 | 3 | Draft
US-021 | Nomination | Nominate candidate | Must | 8 | 3 | Draft
US-022 | Nomination | Quota limit enforcement | Must | 13 | 3 | Draft
US-024 | Nomination | Record host decision | Must | 8 | 4 | Draft
US-009 | Application | Application status tracking | Must | 5 | 4 | Draft
US-033 | Audit | Immutable audit history | Must | 13 | 4 | Draft
US-004 | Opportunity | Requirement version history | Must | 8 | 4 | Draft
US-026 | Pre-departure | Pre-departure checklist | Must | 8 | 5 | Draft
US-032 | Reporting | Operational report | Must | 8 | 5 | Draft
US-035 | Integration | Identity provider authentication | Must | 8 | 1 | Ready
US-036 | Integration | SIS academic data retrieval | Must | 8 | 2 | Draft
US-003 | Opportunity | Define required document set | Must | 5 | 1 | Proposed
US-014 | Validation | Document version history | Must | 5 | 3 | Proposed
US-018 | Review | Record correction requests | Must | 5 | 2 | Proposed
US-025 | Nomination | Nomination vs admission labels | Must | 5 | 4 | Proposed
US-038 | Opportunity | Register partner change proposal | Must | 5 | 5 | Proposed
US-039 | Opportunity | Change impact preview and confirmation | Must | 13 | 5 | Proposed
US-040 | Opportunity | Open new application period | Must | 5 | 5 | Proposed
US-041 | Notification | Notify concerned parties of a return | Must | 5 | 5 | Proposed
US-043 | Nomination | Accept or decline offer | Must | 8 | 4 | Proposed
US-045 | Nomination | Withdraw other applications on acceptance | Must | 8 | 5 | Proposed
US-048 | Application | Several active applications | Must | 3 | 1 | Proposed

## Risk Register
ID | Risk | Probability | Impact | Mitigation | Owner | Status
R-001 | Partner requirements, quotas or deadlines change after an application period has already opened. | High | High | Represent opportunity requirements as immutable versions. A partner proposes a change, the Mobility Coordinator confirms it after an impact preview, and a material change returns all active applications for reapplication in a new period with notices and priority for previously approved students (US-002, US-004, US-038 to US-041). | Product Owner | Open
R-002 | The simulated Student Information System or identity provider is unavailable during validation or demonstration. | Medium | High | Mock integration layer with fixture data; submissions and documents persist independently of validation, which is retried later (US-035, US-036). | Architect | Open
R-003 | Students misread the status vocabulary and confuse institutional nomination with final host admission. | Medium | High | Model nomination and admission as separate decisions with distinct student-facing labels validated with advisers (US-024, US-025). | Business Analyst | Open
R-004 | The quota override policy is still undefined, leaving an unaudited nomination path. | Medium | High | Keep the override behind a single authorized role with a mandatory justification and an audit entry; tracked as open clarification CL-008 (US-023, US-033). | Product Owner | Open
R-005 | Sensitive personal documents such as passports and transcripts are handled insecurely. | Low | High | Synthetic documents and fictitious student data only, restricted role-based access, no production identification files (ASM-009). | QA and privacy owner | Open
R-006 | Scope grows toward inbound mobility, real credit enrolment or real payment processing. | High | High | Explicit out-of-scope list reviewed at each milestone; changes require a recorded scope decision. | Project Manager | Open
R-007 | Academic Program Coordinators are unavailable to validate the equivalency review workflow. | Medium | Medium | Early clarification sessions; record the workflow as an assumption until confirmed (ASM-011). | Project Manager | Open
R-008 | Document expiry rules remain unclear, causing false rejections close to departure. | Medium | Medium | Validate expiry rules with advisers using real document types before implementing the flagging logic (US-015). | Business Analyst | Open
R-009 | Client feedback on open clarifications arrives too late to influence the design. | Medium | Medium | Weekly review meetings; open items tracked visibly in the Clarification Log with their impacted backlog items. | Project Manager | Open
R-010 | Quota counting is ambiguous: it is not defined whether refused, revoked, declined, expired, returned or withdrawn nominations release their places (CL-014). | Medium | High | Parametrize which nomination statuses count as active; confirm the rule with the Mobility Coordinator (US-022). | Business Analyst | Open
R-011 | Storing eligibility as pass/fail with a SIS reference, without raw GPA and credits, may conflict with auditors' needs (CL-017). | Low | Medium | Agree retention rules with the Registrar and IT Services; keep the SIS as the master (US-012, US-036). | Architect | Open
R-012 | The operational report cannot be completed because 'delayed' and 'at-risk' have no agreed definition (CL-016). | High | Medium | Propose thresholds and validate them with the Mobility Coordinator before building US-032. | Business Analyst | Open
R-013 | A single deployment and database is one failure domain for the demonstration. | Medium | Medium | Document the limitation; acceptable for course scope; not a high-availability design. | Architect | Accepted
R-014 | Module boundaries erode inside the modular monolith. | Medium | Medium | Automated dependency check (T-ARCH-01) and code review. | Technical lead | Open
R-015 | Simulated partner portal and notification gateway hide the behaviour of real providers (duplicates, ordering). | Medium | Medium | Contract tests; stable delivery keys; state clearly what the mocks do not prove. | Architect | Open
R-016 | The scholarship representative (STK-07) has no user story or notification defined (CL-018). | Medium | Low | Define stories or record the stakeholder as out of scope. | Product Owner | Open
R-017 | A mistaken or forged confirmation of a partner change returns every application of an opportunity and cannot be undone. | Medium | High | Partner has no platform account; coordinator confirmation after an impact preview; stale-preview check; audit (US-038, US-039). | Architect | Open
R-018 | Returning students already admitted or accepted invalidates partner admissions, visa evidence and student plans (CL-021). | Medium | High | Confirm intent with the Mobility Coordinator and partners; consider a stronger confirmation for these cases. | Product Owner | Open
R-019 | Cross-opportunity cascades (acceptance, return) risk deadlocks or inconsistent places. | Medium | Medium | Documented lock order; concurrency tests T-ACC-01 and T-CHG-02; proof-of-concept steps 5 to 7. | Technical lead | Open
R-020 | The meaning of 'priority' and of 'term' is ambiguous (CL-020, CL-022). | Medium | Medium | Written definitions confirmed with the Mobility Coordinator. | Business Analyst | Open
R-021 | A database superuser can alter the audit history. | Low | High | Residual risk accepted for the demonstration; production would need tamper-evident controls (US-033). | QA and privacy owner | Accepted

## Success Criteria
ID | Success Criterion | Verification
SC-01 | A student can submit a complete outbound mobility application through a single entry point. | Functional demonstration
SC-02 | Applications that do not meet the eligibility requirements of an opportunity are identified automatically. | Test scenarios
SC-03 | No nomination exceeds the available places of an opportunity without a recorded authorized override. | Test scenarios
SC-04 | Every application shows a current status and the next action expected from the student. | Demonstration
SC-05 | Required documents are tracked with version history, and documents expiring before departure are flagged. | Acceptance tests
SC-06 | Institutional nomination and host-university admission are recorded and displayed as two distinct decisions. | Acceptance tests
SC-07 | The academic equivalency review is completed and recorded before a candidate is nominated. | Acceptance tests
SC-08 | Every status transition, decision and override is retrievable from the audit history. | Audit review
SC-09 | A coordinator can identify pending, incomplete, delayed and at-risk applications from one report. | Functional review
SC-10 | A confirmed material change to an opportunity returns all its active applications for reapplication and notifies everyone concerned of the change, the need to redo the process and the new deadline; a non-material change returns none. | Test scenarios
SC-11 | One complete outbound mobility workflow can be demonstrated from publication to pre-departure tracking. | Client acceptance review
SC-12 | A student can hold several active applications, but only one accepted mobility per term; accepting one withdraws the others of that term and releases their places. | Test scenarios
SC-13 | When valid candidates exceed the available places, only candidates chosen by the partner can be nominated, and never beyond the places. | Test scenarios

## Traceability Matrix
Stakeholder | Stakeholder concern | Process problem (AS-IS) | Backlog item | Acceptance criterion | Success criterion
STK-01 | "I cannot tell what is happening with my application or what I still have to do." | Status lives in adviser mailboxes and personal spreadsheets, so students have to ask to find out. | US-009 | Given a submitted application, when the student opens it, then the current status and the next expected action are shown. | SC-04
STK-01 | "I thought being nominated meant I had been accepted." | Nomination and host admission are communicated in the same informal email thread. | US-025 | Given a nominated application, when the student views it, then nomination and host admission appear as two separate decisions. | SC-06
STK-02 | "Students keep submitting incomplete or expired documents." | Documents are checked manually per student, with no record of which version was reviewed. | US-013, US-014, US-015 | Given a required document set, when a document is missing or expires before the start date, then the application is flagged as incomplete. | SC-05
STK-02 | "I spend my time chasing corrections by email." | Correction requests are informal and leave no trace of what was asked or when. | US-018 | Given an incomplete application, when the adviser requests a correction, then the request is recorded against the application and the student is notified. | SC-04
STK-03 | "Requirements from partners change after we have already opened applications." | Requirements are copied into forms and emails, so a change means reissuing information manually. | US-002, US-004, US-038, US-039, US-040, US-041 | Given a partner change classified as material, when the coordinator confirms it after the impact preview, then all active applications of the opportunity are returned for reapplication, a new application period opens and everyone concerned is notified; a non-material change returns none. | SC-10
STK-03 | "We risk nominating more students than the places we actually have." | Quotas are tracked in a spreadsheet maintained in parallel with the nominations. | US-022, US-023 | Given an opportunity with all places taken, when a further nomination is attempted, then it is blocked unless an authorized override with justification is recorded. | SC-03
STK-04 | "Equivalency plans reach me incomplete and too late." | Academic review and international office review are not coordinated, so order and timing vary. | US-019, US-020 | Given a triaged application, when routing runs, then the academic coordinator of the student's programme receives it before nomination is possible. | SC-07
STK-05 | "Nomination dossiers arrive incomplete or after our deadline." | Partner deadlines are held separately from Horizon deadlines and are not centrally visible. | US-031 | Given an opportunity with a partner deadline, when the deadline approaches, then reminders are issued against both Horizon and partner dates. | SC-09
STK-06 | "Academic data must not be duplicated or accessed without control." | GPA and credits are re-typed into forms and spreadsheets by hand. | US-012, US-036 | Given an application under validation, when eligibility is checked, then GPA and credits are read from the SIS and not stored as an independent record. | SC-02
STK-08 | "Overrides and administrative actions must be auditable." | Withdrawals, destination changes and exceptions are documented inconsistently or not at all. | US-033 | Given any status transition, decision or override, when it occurs, then an immutable audit entry with actor, timestamp and reason is created. | SC-08
STK-01 | Team requirement (to be validated with students): apply to several destinations while keeping only one accepted mobility per term. | Not documented in the AS-IS analysis; derived from the Evaluation 2 team requirement. | US-043, US-045, US-048 | Given a student with several active applications in the same term, when the student accepts one offer, then that mobility is recorded as accepted, the other applications of that term are withdrawn and their places released. | SC-12
STK-01 | Team requirement (to be validated with students): after a partner change, be told what changed, what to redo and by when. | Not documented in the AS-IS analysis; derived from the Evaluation 2 team requirement. | US-041, US-042 | Given a returned application, when the student opens it or receives the notice, then it states what changed, that a new application is required and the new deadline, and marks priority where it applies. | SC-10
STK-05 | Team requirement (to be validated with partners): choose among valid candidates when there are more candidates than places. | Not documented in the AS-IS analysis; derived from the Evaluation 2 team requirement. | US-046 | Given more valid candidates than places, when the partner selection is registered, then only the selected candidates can be nominated, within the available places. | SC-13
STK-07 | Being notified too late in the cycle; unclear funding eligibility per destination (from the Stakeholder Register). | To be established. No user story yet (see CL-018). | None yet | To be defined with the stakeholder. | —

## Change Log
Revision 1.1 — changes after Evaluation 2 (Architecture and Design Review)
Cells highlighted in light yellow in the other sheets were changed or added in this revision; clear the highlight after review. New stories, points and sprints are proposals pending validation by the team and the client.
Sheet | Item | Change type | What changed | Reason / source
Functional Requirements | US-010 | Updated | As a Student Applicant, I want to withdraw my application with a recorded reason. A return caused by a confirmed partner change is recorded separately from a withdrawal. | A system-driven return (RETURNED_FOR_REAPPLICATION) must be distinguishable from a student withdrawal in reports and audit (ADR-010).
Functional Requirements | US-011 | Updated | As a Student Applicant, I want to start a new application for a different destination while keeping my other applications, because a destination change is a new application. | Decision: a destination change is a new application; several active applications are allowed (CL-007 refined, CL-024).
Functional Requirements | US-025 | Updated | As a Student Applicant, I want to see clearly whether I have been nominated by Horizon, admitted by the host university, or have accepted the mobility myself. | Acceptance is now a third distinct step after admission (ADR-011).
Functional Requirements | US-026 | Updated | As a Mobility Adviser, I want to track a pre-departure checklist for each student who accepted a mobility, covering visa evidence, insurance and briefing attendance. | The checklist is created when the student accepts the offer, not merely when admitted (ADR-011).
Functional Requirements | US-037 | Updated | As a Mobility Coordinator, I want to record partner decisions, candidate selections and proposed changes through a simulated partner-university portal. | Partner staff have no accounts in the platform; the simulated portal is also the channel for change proposals and selections (ADR-010).
Functional Requirements | US-038 | New | As a Mobility Coordinator, I want to register a change proposed by a partner university for one of its opportunities, so that it is recorded and classified as material or non-material. | Partner changes (R-001, CL-006). Proposed priority: Must.
Functional Requirements | US-039 | New | As a Mobility Coordinator, I want to see an impact preview of a proposed change (applications by state, nominations to revoke, places released, notices to send) and confirm it, so that no application is returned by mistake. | Blast radius of a return (R-017). Proposed priority: Must.
Functional Requirements | US-040 | New | As a Mobility Coordinator, I want to open a new application period when a confirmed material change returns applications, so that affected students can apply again. | Reapplication in a new period (CL-006). Proposed priority: Must.
Functional Requirements | US-042 | New | As a Student Applicant whose approved application was returned by a partner change, I want priority when I apply again, so that I am not penalised for a change I did not cause. | Priority for previously approved students (CL-020). Proposed priority: Should.
Functional Requirements | US-047 | New | As a Student Applicant, I want to correct and resubmit a rejected application while the application period is still open. | Correction after rejection while the period is open (CL-025). Proposed priority: Should.
Functional Requirements | US-048 | New | As a Student Applicant, I want to hold several active applications at the same time. | Several active applications (CL-024). Proposed priority: Must.
Functional Requirements | US-043 | New | As a Student Applicant, I want to accept or decline an offer admitted by a host university within an offer window. | Student acceptance (ADR-011, CL-022). Proposed priority: Must.
Functional Requirements | US-044 | New | As the system, I want to expire offers not answered within the window and release their places. | Offer window (CL-022). Proposed priority: Should.
Functional Requirements | US-045 | New | As the system, I want to withdraw a student's other active applications of the same term, and release their places, when the student accepts a mobility. | One accepted mobility per term (CL-024). Proposed priority: Must.
Functional Requirements | US-046 | New | As a Mobility Coordinator, I want to register the candidates chosen by the partner university, so that only chosen candidates are nominated when valid candidates exceed the places. | Partner chooses among valid candidates (CL-023). Proposed priority: Should.
Functional Requirements | US-041 | New | As the system, I want to notify every concerned party (the student, the responsible adviser, the academic coordinators and the mobility coordinator) of a returned application, stating what changed, that the process must be redone and the new deadline. | Everyone concerned is notified of a return (CL-006). Proposed priority: Must.
Product Backlog | US-003 | Corrected (missing Must story) | Define required document set — 5 pts, sprint 1, status Proposed | Must stories absent from the backlog
Product Backlog | US-014 | Corrected (missing Must story) | Document version history — 5 pts, sprint 3, status Proposed | Must stories absent from the backlog
Product Backlog | US-018 | Corrected (missing Must story) | Record correction requests — 5 pts, sprint 2, status Proposed | Must stories absent from the backlog
Product Backlog | US-025 | Corrected (missing Must story) | Nomination vs admission labels — 5 pts, sprint 4, status Proposed | Must stories absent from the backlog
Product Backlog | US-038 | New | Register partner change proposal — 5 pts, sprint 5, status Proposed | New Must story from the Evaluation 2 rules. Points and sprint are proposals to be re-estimated by the team.
Product Backlog | US-039 | New | Change impact preview and confirmation — 13 pts, sprint 5, status Proposed | New Must story from the Evaluation 2 rules. Points and sprint are proposals to be re-estimated by the team.
Product Backlog | US-040 | New | Open new application period — 5 pts, sprint 5, status Proposed | New Must story from the Evaluation 2 rules. Points and sprint are proposals to be re-estimated by the team.
Product Backlog | US-041 | New | Notify concerned parties of a return — 5 pts, sprint 5, status Proposed | New Must story from the Evaluation 2 rules. Points and sprint are proposals to be re-estimated by the team.
Product Backlog | US-043 | New | Accept or decline offer — 8 pts, sprint 4, status Proposed | New Must story from the Evaluation 2 rules. Points and sprint are proposals to be re-estimated by the team.
Product Backlog | US-045 | New | Withdraw other applications on acceptance — 8 pts, sprint 5, status Proposed | New Must story from the Evaluation 2 rules. Points and sprint are proposals to be re-estimated by the team.
Product Backlog | US-048 | New | Several active applications — 3 pts, sprint 1, status Proposed | New Must story from the Evaluation 2 rules. Points and sprint are proposals to be re-estimated by the team.
Risk Register | R-001 | Updated | Mitigation rewritten around the confirmed-change and return workflow. | Client rule on partner changes (CL-006 answered).
Risk Register | R-007 | Corrected | Reference changed from ASM-006 to the new ASM-011. | ASM-006 concerns adviser assignment, not the equivalency workflow.
Risk Register | R-010 | New | Quota counting is ambiguous: it is not defined whether refused, revoked, declined, expired, returned or withdrawn nominations release their places (CL-014). | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-011 | New | Storing eligibility as pass/fail with a SIS reference, without raw GPA and credits, may conflict with auditors' needs (CL-017). | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-012 | New | The operational report cannot be completed because 'delayed' and 'at-risk' have no agreed definition (CL-016). | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-013 | New | A single deployment and database is one failure domain for the demonstration. | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-014 | New | Module boundaries erode inside the modular monolith. | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-015 | New | Simulated partner portal and notification gateway hide the behaviour of real providers (duplicates, ordering). | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-016 | New | The scholarship representative (STK-07) has no user story or notification defined (CL-018). | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-017 | New | A mistaken or forged confirmation of a partner change returns every application of an opportunity and cannot be undone. | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-018 | New | Returning students already admitted or accepted invalidates partner admissions, visa evidence and student plans (CL-021). | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-019 | New | Cross-opportunity cascades (acceptance, return) risk deadlocks or inconsistent places. | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-020 | New | The meaning of 'priority' and of 'term' is ambiguous (CL-020, CL-022). | Risk identified during the Evaluation 2 architecture review.
Risk Register | R-021 | New | A database superuser can alter the audit history. | Risk identified during the Evaluation 2 architecture review.
Success Criteria | SC-10 | Updated (reversed) | Was: a requirement change does not alter the requirements already applied to submitted applications. | Contradicted the client rule on partner changes (CL-006).
Success Criteria | SC-12 | New | One accepted mobility per student per term. | CL-024.
Success Criteria | SC-13 | New | Partner selection among valid candidates. | CL-023 (interpretation pending confirmation).
Traceability Matrix | STK-03 (partner changes) | Updated (reversed) | Backlog items and acceptance criterion rewritten. Was: the application keeps the requirement version in force at submission. | Contradicted the client rule on partner changes (CL-006).
Traceability Matrix | STK-01 — US-043, US-045, US-048 | New | Team requirement (to be validated with students): apply to several destinations while keeping only one accepted mobility per term. | Covers the new rules
Traceability Matrix | STK-01 — US-041, US-042 | New | Team requirement (to be validated with students): after a partner change, be told what changed, what to redo and by when. | Covers the new rules
Traceability Matrix | STK-05 — US-046 | New | Team requirement (to be validated with partners): choose among valid candidates when there are more candidates than places. | Covers the new rules
Traceability Matrix | STK-07 — None yet | New (gap made visible) | Being notified too late in the cycle; unclear funding eligibility per destination (from the Stakeholder Register). | STK-07 had no backlog item and no traceability row.