## Stakeholder Register
ID | Stakeholder | Category | Interest | Influence | Principal expectations | Main concerns | Initial engagement
STK-01 | Student Applicant | Primary user | High | Low | Find opportunities they qualify for, understand requirements, submit one application, know the current status and the next action expected from them | Information scattered across sources, unclear application status, confusing institutional nomination with final admission, documents rejected late in the process | Interviews and application walkthrough
STK-02 | Mobility Adviser | Primary operational user | High | High | Review submitted applications, verify completeness and supporting documents, request corrections, follow up on deadlines per student | Incomplete or expired documents, manual tracking in spreadsheets and email, no visibility of who is waiting on what | Principal stakeholder meetings
STK-03 | Mobility Coordinator | Operational and governance | High | High | Publish opportunities with their requirements, enforce nomination quotas, nominate validated candidates, coordinate deadlines with partner institutions, confirm partner-proposed changes after an impact preview | Nomination quotas exceeded, overrides taken without justification, partner deadlines conflicting with internal ones, no reliable operational reporting | Principal stakeholder meetings and policy review
STK-04 | Academic Program Coordinator | Academic governance | Medium | High | Review course-equivalency plans, record an academic decision, be consulted before a student is nominated | Equivalency plans arriving incomplete or too late, being held responsible for guarantees outside faculty jurisdiction | Workflow and approval consultation
STK-05 | Partner-University Contact | External stakeholder | Medium | High | Receive complete and timely nominations, communicate admission decisions, propose changes to their destination requirements and quotas through the partner portal simulator, and choose among valid candidates when there are more candidates than places | Incomplete nomination dossiers, missed partner deadlines, Horizon working from out-of-date requirement information | Indirect consultation through the Mobility Coordinator
STK-06 | Registrar / Student Information representative | Supporting and data owner | Medium | Medium | Remain the authoritative source of GPA and completed credits, control how academic record data is accessed | Academic data duplicated or drifting out of sync, unauthorized access to student records | Data ownership and integration consultation
STK-07 | Financial Support / Scholarship representative | Supporting user | Medium | Medium | Identify nominated students who need funding, know decision dates early enough to process support | Being notified too late in the cycle, unclear funding eligibility per destination | Requirements consultation
STK-08 | Horizon University IT Services | Technical stakeholder | High | High | Maintainable architecture, authentication through the institutional identity provider, controlled integrations, secure document storage, full auditability | Sensitive personal documents handled insecurely, fragile integrations with SIS and identity services, weak authorization on override actions | Architecture and security consultation

## Clarification Log
ID | Question | Stakeholder | Client response or current understanding | Impact | Status
CL-001 | Who may submit an international mobility application? | Mobility Coordinator | Enrolled degree-seeking students who meet the minimum GPA and completed-credit thresholds of the specific opportunity. | Roles, eligibility and authentication | Closed
CL-002 | Does submitting an application secure a place at the destination? | Mobility Adviser | No. A place exists only after institutional nomination and a recorded admission decision from the host university. | Lifecycle and student communication | Closed
CL-003 | Is an institutional nomination the same as final admission? | Mobility Coordinator | No. Nomination is Horizon's endorsement of a candidate. Final admission is the host university's decision and may still be refused. | Domain model and status vocabulary | Closed
CL-004 | Do all opportunities share the same eligibility requirements? | Mobility Coordinator | No. Minimum GPA, completed credits, language level and required documents vary per opportunity and destination. | Configurable requirements | Closed
CL-005 | Which system owns authoritative GPA and completed-credit data? | Registrar representative | A simulated Student Information System provides academic record data. The platform must not maintain its own version of it. | Integration boundary | Closed
CL-006 | What happens when a partner changes requirements, quotas or deadlines after the application period has opened? | Mobility Coordinator | Updated rule (Evaluation 2 team decision, to be validated with the Mobility Coordinator): a partner proposes the change through the partner portal simulator and the coordinator confirms it after an impact preview. If the change is material (minimum GPA, completed credits, language level, required documents, application period or destination), all active applications of the opportunity, including nominated, admitted and accepted ones, are returned for reapplication. Students are notified of what changed, that they must redo the process and the new deadline, and a new application period opens with priority for students previously approved. Reapplication starts from scratch; drafts are kept. A non-material change (for example more places, text corrections or a longer deadline) returns nothing. This replaces the earlier understanding (keep the requirements in force at submission, case by case). | Requirement versioning and business rules | Closed – validate with client
CL-007 | Can a student change destination after submitting an application? | Mobility Adviser | Updated: a destination change is a new application (a student may hold several active applications), so eligibility validation and academic review start again for the new application. | Change workflow and audit history | Closed
CL-008 | Who may nominate beyond the available places for an opportunity? | Mobility Coordinator | Only a limited authorized role, and only with a mandatory recorded justification. The exact role remains to be confirmed. | Authorization and auditability | Open
CL-009 | How should documents that expire before departure be handled? | Mobility Adviser | A document valid at upload may expire before the mobility start date. The system must flag it and request an updated version. | Document lifecycle and versioning | Closed
CL-010 | Is the academic equivalency review binding? | Academic Program Coordinator | No. The platform records the review decision, but legal equivalency of courses remains under faculty jurisdiction. | Scope and liability boundary | Closed
CL-011 | What happens if the identity provider or the SIS is unavailable? | IT Services | Submitted applications and uploaded documents must remain safely recorded. Validation and synchronization may be retried later. | Reliability and integration design | Closed
CL-012 | Must the system verify visa validity with immigration authorities? | Mobility Adviser | No. The system records visa status and supporting evidence, but verification with authorities stays outside the platform. | Scope | Closed
CL-013 | Which operational reports are most valuable? | Mobility Coordinator | Applications pending review, incomplete document sets, applications at risk of missing a deadline, nominations awaiting a host decision, and withdrawals by destination. | Reporting scope | Closed
CL-014 | Does a nomination that is refused, revoked, declined, expired or returned, or replaced because the student accepted another mobility, or whose application is withdrawn, release its place? | Mobility Coordinator | Proposed understanding (not confirmed): yes, in every one of those cases the place is released. | Quota counting (US-022, SC-03) | Open
CL-015 | What happens to an application that fails the automatic eligibility check? | Mobility Adviser | Proposed understanding (not confirmed): the application is accepted but flagged as not eligible, cannot advance past triage, and the adviser records the rejection. | Submission behaviour (US-012, SC-02) | Open
CL-016 | How are 'delayed' and 'at-risk' applications defined (days in a state, days before a deadline)? | Mobility Coordinator | No definition yet. Thresholds will be proposed and validated. | Operational report (US-032, SC-09) | Open
CL-017 | May the eligibility result be stored as pass/fail per criterion with a SIS reference and timestamp, without raw GPA and credit values? | Registrar representative | Proposed understanding (not confirmed): yes; the SIS remains the master of academic data. | Auditability versus data ownership (CL-005) | Open
CL-018 | Is the notification gateway a simulated email service, and which role and notices does the scholarship representative (STK-07) need? | Scholarship representative / IT Services | Proposed understanding (not confirmed): simulated email service. The role and notices of STK-07 are still to be defined; there is no user story yet. | Notifications and missing stakeholder coverage | Open
CL-019 | Which partner changes are material, that is, return applications? | Mobility Coordinator | Material: minimum GPA, completed credits, language level, required documents, application period, destination. Non-material: more places, text corrections, a longer deadline. To confirm: a reduction of places or a shortened deadline. Proposal: neither returns applications, and a reduction below the active nominations is refused until nominations are revoked. | Material boundary (US-038, US-039) | Open
CL-020 | What does 'previously approved' mean for priority, and what does priority do? | Mobility Coordinator | Proposed understanding (not confirmed): the returned application had reached academic approval or beyond. Priority is a visible flag and orders the review queues; it does not bind the partner's selection. | Reapplication (US-042) | Open
CL-021 | Should students already admitted or accepted also be returned after a material change? | Mobility Coordinator; partner-university contacts | The team rule says all applications are returned, including admitted and accepted ones. Confirm that this is intended, given the effect on partner admissions, pre-departure data and visa evidence. | Largest impact on students and partners (R-018) | Open
CL-022 | What is the 'period' of the one-accepted-mobility rule, how long is the offer window, and what happens when it expires? | Mobility Coordinator | Proposed understanding (not confirmed): the period is the mobility term of the opportunity (for example 2027-S1). The window length is set per opportunity. On expiry the offer lapses and the place is released. | Acceptance (US-043, US-044, US-045) | Open
CL-023 | How does the partner's choice among candidates relate to the nomination quota? | Mobility Coordinator; partner-university contacts | Interpretation used (not confirmed): Horizon nominates at most as many candidates as places and, if valid candidates exceed the places, only those chosen by the partner; admission remains a later partner decision. Alternative: Horizon nominates more candidates than places and the partner admits among them. | Quota rule (US-022, US-046, SC-03, SC-13) | Open
CL-024 | Can a student hold several active applications, and what happens when the student accepts one? | Mobility Coordinator | Team decision (to validate): yes. After a host admits the student there is an offer window; accepting one offer withdraws the student's other applications of that term and releases their places. | Lifecycle and quota (US-043, US-045, US-048, SC-12) | Closed – validate with client
CL-025 | Can a rejected application be corrected and resubmitted? | Mobility Adviser | Team decision (to validate): yes, while the application period is still open. | Lifecycle (US-047) | Closed – validate with client

## Assumption Log
ID | Assumption | Rationale | Risk if incorrect | Validation method | Owner | Status
ASM-001 | Institutional users will authenticate through a simulated university identity provider. | A semester project cannot use production university credentials. | Medium | Confirm technical constraints with IT Services | Technical lead | Active
ASM-002 | The simulated Student Information System is authoritative for GPA and completed credits. | The platform should not duplicate authoritative academic record data. | High | Confirm data ownership and mock-service contract | Business analyst | Active
ASM-003 | Eligibility and document requirements can be expressed as configurable data per opportunity rather than as code. | Requirements differ per destination and are expected to change during live application cycles. | High | Model three real opportunities with the Mobility Coordinator | Architect | Active
ASM-004 | The requirements in force at submission time remain applicable to that application if the partner later changes them. | Students should not be penalised for a change made after they applied. Recorded as open clarification CL-006. Superseded in Evaluation 2: a confirmed material change now returns all active applications (see CL-006). | High | Confirm policy with the Mobility Coordinator | Business analyst | Superseded
ASM-005 | An institutional nomination must always reference a validated application. | The client clearly distinguishes application, nomination and admission. | High | Validate during lifecycle review | Product owner liaison | Active
ASM-006 | Every mobility opportunity has one responsible mobility adviser. | Current practice assigns advisers by programme and destination. | Medium | Validate against current adviser assignment practice | Business analyst | Active
ASM-007 | Host-university decisions are recorded by staff through a simulated partner portal, not received automatically. | Partner institutions keep their own admission platforms, which are out of scope. | Medium | Confirm that no real partner integration is expected | Technical lead | Active
ASM-008 | A notification failure must not invalidate an otherwise successful submission or nomination. | Notifications are secondary to the consistency of the application record. | High | Confirm expected failure behaviour with client and IT | Architect | Active
ASM-009 | Synthetic documents and fictitious student data will be used throughout the project. | Real passports, transcripts and identification files must not be handled. | Low | Confirm data-handling constraints | QA and privacy owner | Active
ASM-010 | Only outbound mobility is in scope for the first release. | Inbound mobility has a different lifecycle and is not needed to demonstrate the outbound workflow. | Medium | Confirm scope at foundation review | Project lead | Active
ASM-011 | The course-equivalency review workflow (adviser triage, academic coordinator decision, then nomination) is as described by the client. | Academic Program Coordinators have not yet validated it (R-007). | Medium | Clarification sessions with Academic Program Coordinators | Project manager | Active
ASM-012 | Partner staff have no accounts in the platform; they work in the simulated partner portal and the Mobility Coordinator registers their change proposals, candidate selections and decisions. | Partner admission platforms are out of scope (ASM-007) and the security boundary stays small. | Medium | Confirm with the Mobility Coordinator and IT Services that no partner login is expected | Technical lead | Active
ASM-013 | Notifications are sent through a simulated email gateway. | A real mail provider is not needed to demonstrate the workflow. | Low | Confirm with IT Services (CL-018) | Technical lead | Active
ASM-014 | A nomination that is refused, revoked, declined, expired or returned releases its place. | Needed to count the quota consistently. | High | Confirm with the Mobility Coordinator (CL-014) | Business analyst | Active
ASM-015 | The eligibility result is stored as pass/fail per criterion plus a SIS reference and timestamp, not as a copy of GPA or credits. | Keeps the SIS authoritative (CL-005) while preserving traceability. | Medium | Confirm with the Registrar representative and IT Services (CL-017) | Architect | Active

## Change Log
Revision 1.1 — changes after Evaluation 2 (Architecture and Design Review)
Cells highlighted in light yellow in the other sheets were changed or added in this revision; clear the highlight after review. Rows marked 'validate with client' record team decisions that still need the Mobility Coordinator's confirmation.
Sheet | Item | Change type | What changed | Reason / source
Stakeholder Register | STK-03 | Updated | Expectation added: confirm partner-proposed changes after an impact preview. | ADR-010 / client rule on partner changes.
Stakeholder Register | STK-05 | Updated | Partners propose changes (they do not publish directly) and choose among valid candidates. | Partner staff have no platform accounts (ASM-012); CL-023.
Clarification Log | CL-006 | Updated (reversed) | Response replaced; status changed from Open to Closed – validate with client. Previous response: Applications already submitted should keep the requirements in force at submission time, and the coordinator decides case by case. Final policy remains under review. | Client rule on partner changes.
Clarification Log | CL-007 | Updated | Destination change is now a new application. Previous response: Yes, before nomination, but the change restarts eligibility validation and academic review. | Decision on multiple applications (CL-024).
Clarification Log | CL-014 | New | Does a nomination that is refused, revoked, declined, expired or returned, or replaced because the student accepted another mobility, or whose application is withdrawn, release its place? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-015 | New | What happens to an application that fails the automatic eligibility check? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-016 | New | How are 'delayed' and 'at-risk' applications defined (days in a state, days before a deadline)? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-017 | New | May the eligibility result be stored as pass/fail per criterion with a SIS reference and timestamp, without raw GPA and credit values? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-018 | New | Is the notification gateway a simulated email service, and which role and notices does the scholarship representative (STK-07) need? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-019 | New | Which partner changes are material, that is, return applications? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-020 | New | What does 'previously approved' mean for priority, and what does priority do? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-021 | New | Should students already admitted or accepted also be returned after a material change? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-022 | New | What is the 'period' of the one-accepted-mobility rule, how long is the offer window, and what happens when it expires? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-023 | New | How does the partner's choice among candidates relate to the nomination quota? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-024 | New | Can a student hold several active applications, and what happens when the student accepts one? | Raised or decided during the Evaluation 2 architecture review.
Clarification Log | CL-025 | New | Can a rejected application be corrected and resubmitted? | Raised or decided during the Evaluation 2 architecture review.
Assumption Log | ASM-004 | Updated (reversed) | Status Active → Superseded; rationale notes the replacement. | Client rule on partner changes (CL-006).
Assumption Log | ASM-011 | New | The course-equivalency review workflow (adviser triage, academic coordinator decision, then nomination) is as described by the client. | Needed by the Evaluation 2 design.
Assumption Log | ASM-012 | New | Partner staff have no accounts in the platform; they work in the simulated partner portal and the Mobility Coordinator registers their change proposals, candidate selections and decisions. | Needed by the Evaluation 2 design.
Assumption Log | ASM-013 | New | Notifications are sent through a simulated email gateway. | Needed by the Evaluation 2 design.
Assumption Log | ASM-014 | New | A nomination that is refused, revoked, declined, expired or returned releases its place. | Needed by the Evaluation 2 design.
Assumption Log | ASM-015 | New | The eligibility result is stored as pass/fail per criterion plus a SIS reference and timestamp, not as a copy of GPA or credits. | Needed by the Evaluation 2 design.